TECHWISE

Smart E-Commerce & Product Intelligence Platform

PROJECT PLANNING & MANAGEMENT

Falcon Team
DEPI Graduation Project
Planning Window: 2–16 October 2026
Submission Deadline: 16 October 2026

WORKING DRAFT — REVIEW REQUIRED

Prepared from confirmed TechWise project context and the supplied DEPI guidelines. Proposed assignments and KPI targets require team approval.

# 1. Document Control

| Field | Value |
| --- | --- |
| Project | TechWise — Smart E-Commerce & Product Intelligence Platform |
| Team | Falcon Team |
| Document | Project Planning & Management |
| Planning window | 2 October 2026 – 16 October 2026 |
| Submission deadline | 16 October 2026 |
| Status | Working draft; proposed assignments and KPI targets require team review |

# 2. Executive Summary

TechWise is a smart e-commerce and product-intelligence platform designed to support the product lifecycle beyond a conventional online store: Discover → Understand → Compare → Decide → Buy → Own → Upgrade → Resell → Transfer.

The platform combines AI-assisted shopping, product intelligence, compatibility information, purchase decision support, product-truth mechanisms, lifecycle management, and a verified second-life marketplace.

Planning principle: AI supports intent understanding, explanation, recommendation, and summarization. Deterministic backend services and database records remain responsible for validation, business rules, compatibility decisions, calculations, authorization, ownership, and factual product state.

# 3. Project Proposal

## 3.1 Problem Statement

Conventional e-commerce experiences often focus on product discovery and checkout. Buyers may still need to research specifications, compare alternatives, understand compatibility, evaluate product claims, and decide whether to buy, upgrade, or resell. Second-life transactions also need clear eligibility and ownership-history rules. TechWise aims to bring these decision and lifecycle activities into one coherent platform.

## 3.2 Project Objectives

Help users discover products through structured search, filtering, and AI-assisted natural-language intent understanding.

Present product information to support understanding and comparison.

Support purchase decisions using explicit requirements, compatibility information, and deterministic decision logic.

Separate recorded product facts from AI-generated explanations and recommendations.

Support a second-life marketplace subject to platform-origin, current-ownership, listing-eligibility, and dispute checks.

Preserve product-asset history across resale while changing ownership records and protecting previous owners’ personal information.

## 3.3 Scope — In Scope

AI Shopping Intelligence.

Verified Second-Life Marketplace.

Product Compatibility Graph.

Purchase Decision Engine.

Product Truth Layer.

Buy vs Upgrade vs Resell Engine.

Advanced Smart Filtering as a cross-cutting capability, not a separate core feature.

Responsive UI planning for desktop and mobile screen variants.

## 3.4 Scope — Not Yet Confirmed / Exclusions

Specific payment gateway, hosting provider, AI model/provider, database engine, framework, or authentication provider unless formally selected.

Claims of physical platform verification unless a corresponding process is implemented.

Unapproved features beyond the confirmed core scope.

Treating AI output as authoritative product facts, eligibility, ownership, or compatibility.

## 3.5 Primary Stakeholders

End customers: discover, compare, decide, buy, own, upgrade, and resell products.

Second-life sellers: list eligible products and provide required evidence.

Second-life buyers: evaluate condition, provenance, and available evidence.

Platform administrators/moderators: review listings, disputes, and policy compliance.

Falcon Team: plan, design, implement, test, document, and present the system.

DEPI instructors/evaluators: assess planning, requirements, design, implementation, testing, documentation, and presentation.

# 4. Project Plan

## 4.1 Delivery Approach

The team will work cross-functionally. Work is divided by screens, features, modules, and deliverables rather than isolating members into permanent UI-only, backend-only, database-only, or testing-only silos. Each task should have one accountable coordinator/reviewer, while implementation and validation may involve multiple members.

## 4.2 Schedule and Milestones

| Workstream | Start | Deadline | Milestone / evidence |
| --- | --- | --- | --- |
| Project Planning & Management | 2 Oct 2026 | 16 Oct 2026 | Proposal, plan/Gantt, roles, risk plan, KPIs uploaded to GitHub |
| Literature Review | 9 Oct 2026 | 16 Oct 2026 | Relevant prior work and evaluation/improvement notes documented |
| Requirements Gathering | 9 Oct 2026 | 16 Oct 2026 | Stakeholders, user stories/use cases, functional and non-functional requirements |
| System Analysis & Design | 9 Oct 2026 | 6 Nov 2026 | Architecture, required diagrams, data model, UI/UX prototypes and guidelines |
| Implementation | 16 Oct 2026 | 30 Nov 2026 | Integrated source code and executable/deployed demonstration as feasible |
| Final Presentation, Testing & Reports | 16 Oct 2026 | 4 Dec 2026 | Test evidence, user/technical docs, presentation and final report |

## 4.3 Near-Term Work Plan

| Date | Activity | Exit condition |
| --- | --- | --- |
| 10 Oct | Inventory existing documents and decisions | Existing work classified complete / partial / missing |
| 10–12 Oct | Complete proposal, scope, schedule, coordination model | Draft reviewed by team lead and members |
| 12–14 Oct | Complete risk register and measurable KPIs | Risk owners and measurement methods defined |
| 14–15 Oct | Consistency review and GitHub packaging | Dates, scope, terminology consistent; files readable |
| 16 Oct | Submit planning package and other due phase deliverables | Required documents uploaded; repository link checked |

## 4.4 Resource Allocation

Primary resources are the six Falcon Team members, their development/design tools, the shared GitHub repository, project documentation, and UI prototypes in progress. Specific technology choices and external service costs remain unconfirmed and must not be presented as committed resources until approved.

# 5. Task Assignment & Roles

Operating model: all six members contribute across UI/UX, frontend, backend, data, testing, integration, and documentation according to task needs. Assignments below define coordination/accountability, not exclusive technical silos. Proposed coordination assignments must be reviewed and accepted by the named members before being treated as final.

| Member | Coordination responsibility (proposed) | Shared contributions |
| --- | --- | --- |
| Elshafei Mohamed (Team Leader) | Overall planning, scope and decision tracking; AI module ownership; integration follow-up; final consistency review | Cross-functional implementation, testing, documentation, presentation |
| Hagar Atef | Coordinate an assigned feature/screen package and track acceptance criteria | UI/UX, implementation, testing, documentation, integration |
| Shahd Mohamed | Coordinate an assigned feature/screen package and track acceptance criteria | UI/UX, implementation, testing, documentation, integration |
| Samer Walid | Coordinate an assigned feature/screen package and track acceptance criteria | UI/UX, implementation, testing, documentation, integration |
| Mostafa Mohamed | Coordinate an assigned feature/screen package and track acceptance criteria | UI/UX, implementation, testing, documentation, integration |
| Mohamed Alaa El-Din Fathallah Nafea | Coordinate an assigned feature/screen package and track acceptance criteria | UI/UX, implementation, testing, documentation, integration |

Important: specific feature/screen ownership for the five non-lead members is intentionally left for team confirmation rather than guessed. Once the UI/screen inventory and module boundaries are finalized, assign a task-level owner, reviewer, due date, and acceptance criteria to each item.

## 5.1 Team Working Rules

Use one branch per person plus main, as previously chosen; do not introduce a develop branch unless the team explicitly changes this decision.

Break work into reviewable tasks with an owner, deadline, dependencies, and acceptance criteria.

Keep main in a reviewable state and use the team’s agreed review process.

Record material scope, architecture, data, AI-boundary, and business-rule decisions in project documentation.

Do not mark a task complete until its output has been reviewed and relevant evidence is available.

# 6. Risk Assessment & Mitigation Plan

| ID | Risk | Likelihood | Impact | Mitigation / response | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Overlapping planning and requirements deadlines reduce review time | High | High | Prioritize deadline-bound documents; short check-ins; set review cutoff before submission | Team Leader + all members |
| R2 | Scope grows beyond team capacity | Medium | High | Protect six confirmed core features; treat additions as proposals requiring approval | Team Leader |
| R3 | UI prototypes are mistaken for implemented/integrated features | Medium | High | Track design, implementation, integration, and testing as separate statuses | Feature coordinators |
| R4 | AI-generated statements are treated as factual product data | Medium | High | Require structured outputs and backend validation; facts come from product records or verified sources | AI Module Owner + backend contributors |
| R5 | Compatibility or decision logic differs across UI and backend | Medium | High | Keep validation, ranking, compatibility, and calculations in deterministic services; define contracts and tests | Feature coordinators |
| R6 | Second-life listing bypasses origin/ownership/eligibility checks | Medium | High | Validate platform origin, current ownership, listing state, eligibility, and blocking disputes | Second-Life coordinator (to assign) |
| R7 | Previous owner’s personal data is exposed after resale | Low–Medium | High | Separate ownership history from personal data; do not expose previous owners’ private information | Team Leader + data/security contributors |
| R8 | Late integration causes conflicting interfaces or broken flows | Medium | High | Agree contracts early; integrate continuously; maintain blocker list and regression checks | All members |
| R9 | Unconfirmed technologies are documented as final decisions | Medium | Medium | Label undecided choices pending; approve stack/service decisions before marking final | Team Leader + team |
| R10 | GitHub documentation is stale or missing | Medium | Medium | Keep one source of truth; check file links and dates before each milestone | Documentation coordinator (to assign) |

# 7. Key Performance Indicators (KPIs)

The following are proposed project-management and product-quality KPIs. Numerical targets are draft targets for team approval, not DEPI-mandated values.

| KPI | Proposed target | Measurement | Review point |
| --- | --- | --- | --- |
| Planning deliverable completion | 100% of planning artifacts reviewed by 15 Oct | Checklist: proposal, plan, roles, risks, KPIs | Before submission |
| Milestone adherence | At least 90% of planned tasks completed by due date | Tasks completed on time ÷ tasks due | Weekly |
| Task traceability | 100% of active tasks have owner, due date, acceptance criteria | Review task list/repository issues | Weekly |
| Integration health | No known release-blocking issue unresolved at milestone review | Blocker list and integration test results | Milestone reviews |
| Core-flow test coverage | All agreed critical journeys have documented test cases before final testing closes | Test plan mapped to core features | Implementation/testing |
| AI factual-boundary compliance | All AI-dependent flows define validation/source-of-truth rules before acceptance | Review AI contracts and tests | Design/integration |
| Second-life eligibility | All listing acceptance tests cover origin, current ownership, listing state, eligibility, disputes | Requirements-to-test traceability | Feature acceptance |
| Responsive design coverage | Every approved screen has desktop/mobile counterpart except explicitly mobile-only screens | Compare screen inventory with prototypes | Design review |
| Documentation freshness | All milestone documents updated before related submission | Repository and commit review | Every milestone |

# 8. Monitoring, Communication & Change Control

## 8.1 Progress Monitoring

Maintain a shared task list with statuses: Not Started, In Progress, Blocked, In Review, Done.

Review progress, blockers, dependencies, and deadlines at least twice per week during the planning window.

Use evidence-based status: a design is not implementation; local implementation is not integration; a passing test applies only to tested scope.

## 8.2 Change Control

Record proposed changes to scope, deadlines, responsibilities, data rules, AI boundaries, and architecture.

Assess impact on schedule, dependencies, testing, and documentation before accepting a change.

Only explicit team decisions convert a proposal into a confirmed decision.

Update affected documents and the decision log after approval.

## 8.3 Communication and Repository

GitHub is the shared destination for project documents, as required by the supplied DEPI guidance.

Use meaningful commit messages and keep document versions identifiable.

At each submission, verify repository URL, file paths, readability, and latest commit.

Repository URL: insert the actual URL; it was not available in the context used for this draft.

# 9. Acceptance Checklist

Project Proposal: overview, objectives, and scope are explicit.

Project Plan: timeline/Gantt representation, milestones, deliverables, and resource allocation are included.

Task Assignment & Roles: all six members are named; proposed coordination assignments are confirmed.

Risk Assessment: risks include likelihood, impact, mitigation, and owner.

KPIs: each KPI has a definition, target, measurement method, and review point.

Cross-document consistency: dates, feature names, ownership rules, AI boundaries, and scope agree.

Repository: required files are uploaded to GitHub and the link is verified.

Team review: placeholders and proposed targets are approved or explicitly marked pending.

# 10. Open Items Requiring Team Confirmation

Confirm the exact DEPI track name and any instructor template/rubric.

Insert the actual GitHub repository URL and folder structure.

Approve task-coordination assignments for the five non-lead members.

Approve or revise proposed KPI targets.

Confirm formally approved technology-stack decisions; do not infer them from prototypes.

Confirm whether the instructor expects one combined document or separate files for each planning artifact.

# Appendix A — Planning Dates Source

The schedule follows the DEPI Project Documentation Guidelines supplied in the project context: Project Planning & Management (2–16 Oct 2026); Literature Review (9–16 Oct 2026); Requirements Gathering (9–16 Oct 2026); System Analysis & Design (9 Oct–6 Nov 2026); Implementation (16 Oct–30 Nov 2026); Final Presentation, Testing & Reports (16 Oct–4 Dec 2026). The guidance states that all documents should be uploaded to GitHub.